## Dashboard
AUTOMATION & SECURITY ACADEMY — OVERVIEW
Goal: first job as Automation Engineer → Security Automation Engineer
TICKETS
Total tickets | 3
Completed (Done) | 3
In progress (In Progress + Code Review) | 0
Blocked | 0
% completed | 100%
TIME & CONSISTENCY
Total hours worked | 18
Average hours / week | 9
Weekly interviews completed | 2
Weekly reports submitted | 2
SKILLS
Average skill level | 0.75
Target level (average) | 3.4
Skills at or above target | 1
Total skills | 20

## Tickets
TICKETS — work assignments
Ticket ID | Title | Phase | Week | Category | Status | Completion date | GitHub link | Notes / code review feedback
TICKET-001 | Create learning-log repository | 1 | 0 | Process | Done | 2026-07-08 | https://github.com/RadiiYevstratov/learning-log | Remediation: push, week-00 gaps, git mv tracker to repo root, concrete goal in README
TICKET-002 | SSH Brute-Force Detector (diagnostic) | 1 | 1 | Security Automation | Done | 2026-07-12 | https://github.com/RadiiYevstratov/ssh-bruteforce-detector | 5 code review rounds. Key lessons: bare except, sys.argv, exit codes, refactor global -> return/parameters, testing error paths, complete delivery
TICKET-003 | SSH Detector v2 — sliding time window | 1 | 1 | Security Automation | Done | 2026-07-14 | https://github.com/RadiiYevstratov/ssh-bruteforce-detector | 5 code review rounds. Key lessons: datetime parsing in one place, sort before analysis, window anchored via enumerate (not .index), max per IP, output validation against acceptance criteria — pre-delivery checklist

## Weeks
WEEKLY REPORTS
Week | Start date | Hours worked | Main topic (theory) | Project / ticket | Security topic | Interview completed | Report in learning-log | Mentor notes
0 | 2026-07-06 | 9 | Python basics, WSL setup, Git remote/SSH keys | TICKET-001, TICKET-002 (SSH Brute-Force Detektor) | SSH brute-force, log analysis, data sanitization, public/private key | Yes | Yes | Strong: experiments, design decisions. Weak: delivery discipline (code+output+git log), incremental commits
1 | 2026-07-13 | 9 | datetime + timedelta, argparse, enumerate, sliding window, while over positions | TICKET-003 (SSH Detector v2) | Sliding window detection, slow attacker, false negative, fixed blocks vs. sliding window | Yes | Yes | Strong: algorithm (paper walkthrough, counterexample in interview). Weak: pre-delivery validation — defaults survived 4 rounds; pre-delivery checklist introduced
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51

## Skills
SKILLS MATRIX — rating 0 to 5
0 = nothing, 1 = heard of it, 2 = basics, 3 = can use with help, 4 = independent, 5 = can explain to a junior
Skill | Area | Current level (0–5) | Target for junior role | Last updated | Evidence (project / repo)
Python | Core | 3 | 4 | 2026-07-14 | https://github.com/RadiiYevstratov/ssh-bruteforce-detector (v2: datetime, argparse, sliding window)
Linux | Core | 2 | 4 | 2026-07-12 | WSL setup + auth.log analysis (TICKET-002)
Git | Core | 3 | 4 | 2026-07-12 | https://github.com/RadiiYevstratov/learning-log
HTTP | Web/API | 0 | 3
REST API | Web/API | 0 | 4
SQL | Data | 3 | 3
Docker | Infra | 0 | 3
Networking | Infra | 2 | 4
Windows | Infra | 0 | 3
Active Directory | Infra | 0 | 3
Azure | Cloud | 0 | 3
Cloud concepts | Cloud | 0 | 3
SIEM | Security | 0 | 3
Security Automation | Security | 0 | 4
Microsoft Security Stack | Security | 0 | 3
DevSecOps | Security | 0 | 3
Clean code / code review | Engineering | 1 | 4
Testing | Engineering | 0 | 3
CI/CD | Engineering | 0 | 3
Documentation / README | Engineering | 1 | 4
Average |  | 0.75 | 3.4

## Roadmap
ROADMAP — 12 months
Phase | Months | Focus | Key outputs (portfolio) | Status
1 | 1–3 | Python + Linux + Git as working tools | Log parser, file automation, security scripts, learning-log | In Progress
2 | 4–6 | REST API, HTTP, SQL, Docker | API automation (Defender-style), own API, dockerized project | To Do
3 | 7–9 | Azure, Windows/AD, SIEM concepts | Cloud automation, detection rules, alerting pipeline | To Do
4 | 10–12 | DevSecOps, CI/CD, job market preparation | CI/CD pipeline, portfolio polish, German CV, interview training | To Do